## Sheet1
User Stories Smart Parking
User Story Id | As a | I want to | So that | Test Case | Priority | Estimate Effort(Dev)(hrs) | Estimate Efforts (QA)(hrs) | Total Efforts(hrs)
US-001 | User / Owner | Register for an account | I can access the smart parking system | Verify that a user can successfully register with valid details. Validate error handling for duplicate or invalid input. | High | 4 | 1 | 5
US-002 | User / Owner | Log in with my credentials | I can access the system’s services | Verify login with valid credentials. Check incorrect password handling. Ensure session timeout works as expected. | High | 4 | 1 | 5
US-003 | User | Serach for parking spot | I can see the parking details and book it | Verify that a user can search for available parking spots based on location, time, and availability. Ensure search results update dynamically when availability changes. | High | 12 | 2 | 14
US-004 | User | See my past and current booking | I can veiw my past and current booking details | Verify that a user can see a list of past and current bookings. Validate the display of booking details (e.g., date, time, price, location). Ensure filtering by date and status (active, expired, canceled) works correctly. | Medium | 3 | 1 | 4
US-005 | User/Owner | See my user profile | I can veiw and edit personal details | Verify that a user can view their profile details. Ensure the user can edit personal information and save changes. Validate email and phone number formats during updates. | Medium | 4 | 2 | 6
US-006 | Owner | See booking details for my parking spot | I can veiw my booking details | Ensure an owner can see all bookings for their listed parking spots. Verify that booking details are accurate, including user info, time, and status. Validate filtering by date and booking status. | High | 4 | 1 | 5
US-007 | User | See the parking details | I can make a decision to book a spot | Verify that parking details such as location, price, availability are displayed correctly. Ensure users can see ratings and reviews before booking. Validate navigation to the booking page. | High | 2 | 1 | 3
US-008 | Owner | Add my owned parking spot | I can list my owned parking spot on the app | Ensure an owner can successfully add a parking spot with all required details (location, price, availability). Validate image upload functionality for parking spots.(Optional) Check for duplicate listings. | High | 6 | 2 | 8
US-009 | User | Book a parking spot | I can reserve the parking slot | Verify that a user can successfully book an available parking spot. Ensure real-time availability updates during booking. Validate email confirmation upon booking. | High | 4 | 1 | 5
US-010 | User | Pay for my booking | I can confirm my paking slot | Verify that users can make payments using different payment methods (credit card, UPI, wallet, etc.). Ensure successful transactions update the booking status. Validate handling of failed transactions. | High | 10 | 3 | 13
US-011 | User | Give feedback and ratings | Other people can use my experience | Verify that a user can submit ratings and feedback after using a parking spot. Ensure only users who completed a booking can leave reviews. Validate moderation of inappropriate content in feedback. | Medium | 3 | 1 | 4
US-012 | Owner | Leave feedback and ratings | Other people can use my experience | Ensure that owners can submit ratings and feedback about users. Verify feedback visibility to users. Validate that ratings impact user reputation. | Medium | 3 | 1 | 4
[6 empty] | Total |  | 76